# Cell C-Phase I Construction Documentation Report

Montmorency-Oscoda-Alpena Solid Waste Management Authority

Atlanta, Michigan

October 1, 2026

Prepared by:

Gosling Czubak Engineering Sciences, Inc.

1280 Business Park Drive

Traverse City, Michigan

(231) 946-9191

www.goslingczubak.com

Daniel J. Thomas, P.E. 	Adam E. Segerlind, P.E.
Project Engineer	CQA Officer

GCES Project # 250008.07 (construction contract 260006.07)

document1

Table of Contents

1.0	Introduction	1

1.1	Construction Schedule	1

2.0	Construction roles & responsibilities	2

3.0	Subgrade & Site Preparation	4

3.1	Certification & Acceptance	6

4.0	Secondary liner system	7

4.1	Geosynthetic Clay Liner (GCL)	8

4.1.1	Prequalification Data	8

4.1.2	Delivery & Storage	10

4.1.3	Deployment	10

4.1.4	Seaming	10

4.1.5	In Place Testing	10

4.1.6	Geosynthetic Clay Liner Acceptance	11

4.2	Geomembrane	12

4.2.1	Prequalification Data	12

4.2.2	Delivery & Storage	14

4.2.3	Deployment	14

4.2.4	Seaming	15

4.2.5	Defects & Repair	17

4.3	Geocomposite	17

4.3.1	Prequalification Data	17

4.3.2	Delivery & Storage	2

4.3.3	Deployment	2

4.3.4	Seaming	3

4.3.5	Defects & Repair	3

4.4	Leak Detection System	4

4.4.1	Prequalification Data	4

4.4.2	Placement	5

4.4.3	Testing	6

4.4.4	Defects & Repair	6

5.0	Primary Liner System	6

5.1	Geosynthetic Clay Liner (GCL)	7

5.1.1	Prequalification Data	7

5.1.2	Delivery & Storage	7

5.1.3	Deployment	7

5.1.4	Seaming	8

5.1.5	Defects & Repair	8

5.2	Geomembrane	8

5.2.1	Deployment	8

5.2.2	Seaming	9

5.2.3	Defects & Repair	10

5.3	Geocomposite	10

5.3.1	Deployment	2

5.3.2	Seaming	2

5.3.3	Defects & Repair	3

5.4	Leachate Collection System	3

5.4.1	Prequalification Data	3

5.4.2	Placement	4

5.4.3	Testing	4

5.4.4	Defects & Repair	5

5.4.5	Final Acceptance	5

6.0	Additional Project Details	5

6.1	Anchor Trench	5

6.2	Rain Flap	5

6.3	Drainage	6

7.0	Operating License Application	6

Tables

Table 1 Construction Schedule	2

Table 2 Roles & Responsibilities	3

Table 3 Subgrade Material Properties	5

Table 4 GCL Prequalification Data Summary	9

Table 5 GCL Conformance Testing Results	11

Table 6 Interface Friction Results Summary	13

Table 7 Seaming Personnel & Equipment	16

Table 8 Secondary Geocomposite Roll List	4

Table 9 Secondary Drainage Sand Prequalification Summary	5

Table 10 Drainage Stone Prequalification Summary	6

Table 11 Primary Geocomposite Roll List	2

Table 12 Primary Drainage Sand Particle Size Distribution (Revised)	3

Attachments

Att. 1	Record Drawings

Att. 2	Construction Observation Reports

Att. 3	EGLE Correspondence and Project Administration Records

Att. 4	Subgrade Material Properties

Att. 5	Density and Thickness Verification Test Records

Att. 6	Subsurface Soil Acceptance Forms

Att. 7	Geosynthetic Clay Liner Prequalification Submittals

Att. 8	Geosynthetic Clay Liner Shipping Papers

Att. 9	Geosynthetic Clay Liner Placement and Repair Records

Att. 10	Geomembrane Prequalification Submittals

Att. 11	Interface Friction Test Results

Att. 12	Geomembrane Shipping Papers

Att. 13	Secondary Geomembrane Panel Placement and Seaming Summary

Att. 14	Secondary Geomembrane Non-Destruct Test Records

Att. 15	Secondary Geomembrane Destruct Test Results

Att. 16	Secondary Geomembrane Repair Records

Att. 17	Geocomposite and Filter Geotextile Prequalification Submittals

Att. 18	Geocomposite and Filter Geotextile Shipping Papers

Att. 19	Sand Prequalification Data

Att. 20	Drainage Stone Prequalification Data

Att. 21	Leachate Pipe Material Submittals and Fusion Qualifications

Att. 22	Pipe Fusion and Pressure Test Records

Att. 23	Primary Geomembrane Panel Placement and Seaming Summary

Att. 24	Primary Geomembrane Non-Destruct Test Records

Att. 25	Primary Geomembrane Destruct Test Records

Att. 26	Primary Geomembrane Repair Records

Att. 27	Leachate Building, Pumps, Controls and Force Main Records

Att. 28	License Application

# Introduction

This Construction Documentation Report (CDR) has been prepared for the Montmorency-Oscoda-Alpena (MOA) Landfill to document the construction of landfill Cell C - Phase I.  This CDR meets the requirements of the Construction Quality Assurance (CQA) Plan and Part 115, Solid Waste Management, of the Michigan Natural Resources and Environmental Protection Act, Public Act 451 of 1994, as amended (Part 115).  The CQA Plan, dated June 24, 2026, provides the basis of the testing, documentation, and record keeping required to ensure that the landfill cell is built in accordance with the design criteria and specifications in the Landfill Expansion Construction Permit Application (Engineering Report, June 1998), 2012 Permit Revisions, and the 2026 Permit Upgrade – Cell C Liner System (GCES Project No. 260006, approved June 29, 2026). Construction contract documents are tracked as GCES Project No. 260006.07.

The following information was used in the development of this documentation report and accompanying record drawing set:

- Daily field reports

- Construction staking

- Record surveys

- Photographs

- Material submittals

- Field testing data

- Laboratory testing data

The above information is provided in the attachments referenced in the relevant sections of the CDR.  The record drawings are provided in Attachment 1 in half size and separately as full-size prints.  The construction observation reports are included in chronological order in Attachment 2.  Written correspondence with the Michigan Department of Environment, Great Lakes, and Energy (EGLE) regarding cell construction is found in Attachment 3.

## Construction Schedule

MOA awarded the construction work to M&M Excavating Company, Inc. of Gaylord, Michigan on February 27, 2026 (Agreement effective date, EJCDC C-550). The Contract required Substantial Completion by July 31, 2026, and readiness for final payment by September 15, 2026. The as-built Substantial Completion date is September 30, 2026, pending an executed EJCDC C-625 certificate.  The project completion was delayed beyond the originally anticipated completion date due, in part, to the following:

- Delays in delivery of geomembrane from the manufacturer

- Numerous precipitation events during installation of primary liner system

A summary of the installation schedule is provided below in Table 1.

Table 1 Construction Schedule

Feb

Mar

Apr

May

Jun

Jul

Aug

Sep

Oct

Contract Award
Fri 2/27

Mobilization
Mon 2/16 - Mon 3/23

Diversion Ditches
Wed 3/25 - Wed 4/22

Secondary Liner System
Mon 7/20 - Wed 9/2

Primary Liner System
Mon 7/20 - Wed 9/2

Sand Drainage Layer Installation
Tue 9/8 - Mon 9/14

Finish
Sat 10/10

Start
Mon 2/16

Subgrade & Prep
Wed 3/25 - Wed 4/22

Access Road
Wed 3/25 - Wed 4/22

GCL Installation
Mon 7/20 - Wed 9/2

Geomembrane Installation
Mon 7/20 - Wed 9/2

Substantial Completion
Wed 9/30

Note: Survey certification (three mobilizations), final grade certification survey, and anchor trench construction are not shown; these activities have no scheduled dates in the contract schedule and remain to be determined.

# Construction roles & responsibilities

The construction, testing, and certification roles and responsibilities required by the CQA Plan were completed by the following companies:

Table 2 Roles & Responsibilities

| Role/Responsibility | Company |
| --- | --- |
| Owner | Connie Gerrie, Administrator William Peterson, Chairman (Agreement signatory) MOA Solid Waste Management Authority 6751 Landfill Road, P.O. Box 13 Atlanta, MI 49709 |
| CQA Officer | Adam Segerlind, P.E. Gosling Czubak Engineering Sciences, Inc. 1280 Business Park Drive Traverse City, MI 49686 |
| Resident Project Representative (RPR) | Kyle Bridges Gosling Czubak Engineering Sciences, Inc. 1280 Business Park Drive Traverse City, MI 49686 |
| Construction Contractor | Luke Gordon, VP of Project Management Kenneth P. Nowicki, CEO (Agreement signatory) M&M Excavating Company, Inc. 17 Old State Road Gaylord, MI 49735 |
| Geosynthetic Installer | Matt Sondrol Clean Air and Water Systems, LLC 1323 Poplar Dr. Waukesha, WI 53188 |
| Geosynthetic Testing Laboratory | TRI Environmental, Inc. 9063 Bee Caves Road Austin, TX 78733 |
| Soil Testing Laboratories | Martin Graf, P.E. Gosling Czubak Engineering Sciences, Inc. 1280 Business Park Drive Traverse City, MI 49686 |
|  | Soils & Structures, Inc. 1411 Trade Centre Drive Traverse City, MI 49696 |
|  | Bowser-Morner, Inc. 4518 Taylorsville Road, P.O. Box 51 Dayton, OH 45401 |
|  | Geotechnics, Inc. 544 Braddock Ave. East Pittsburgh, PA 15112 |
| Survey Certification | Mike Stocking, P.S. Gosling Czubak Engineering Sciences, Inc. 1280 Business Park Drive Traverse City, MI 49686 |

# Subgrade & Site Preparation

M&M Excavating began site preparation activities on March 25, 2026.  Site preparations activities included:

- Construction of stormwater diversion berms

- Excavation of native materials to meet design grade

- Placement and compaction of fill soils to meet design grade

- Construction of a new access road

Earthen embankments were constructed along the perimeter of the existing landfill Cells B-1 and Future Cell C-II to prevent stormwater flowing across the interim cover of these cells from entering the construction area.  An excavator with a rubber cutting edge, which was installed to reduce the risk of tearing existing geomembrane, was used to remove overburden from along the interim cell berms and construct the stormwater diversion berms.

Some additional overburden, which was primarily located along the floor of future Cell C – Phase I, was used as fill material for the northern portion of the future cell. These unscreened native soils were used to within 2’ of the final elevation of the subgrade.  Use of native soils in this way was a change from the original CQA Plan; documentation of approval of this change is provided in emails dated June 15 and June 23, which are included in Attachment 3.  A calculated 29,850 cubic yards of material was removed from within the Cell C – Phase I boundary.  ±13,200 cubic yards of fill material was placed within the cell boundary.

Native soils that met the requirements of Table 4-A in the CQA Plan were used in the upper 2’ of subgrade.  Grain size, ASTM D2487, and Modified Proctor, ASTM D1557, test results for the installation of subgrade soils are provided in Attachment 4 and summarized in Table 3.

Table 3 Subgrade Material Properties

| Mod. Proctor (lbs/ft3) | USCS Classification |
| --- | --- |
| 131.2 122.1 118.2 | Sand, Poorly Graded (SP) |

Subgrade material was placed using haul trucks and bulldozers.  The required minimum density of 95% of the standard Proctor maximum dry density (ASTM D698) was achieved by tracking equipment over the placed material.  A Caterpillar D6T bulldozer was used to maintain a loose lift thickness no greater than 12”.  The D6T dozer, with an operating weight of 47,138 pounds, was used to compact the subgrade, which resulted in an in-place thickness of ±9”.  The compacted, in-place density of the subgrade material was determined using a Troxler Model 3440 nuclear density gauge by ASTM Method D6938.  At least one density measurement per lift was collected by the RPR on an approximately 100’ by 100’ grid.  Subgrade density measurements, which were taken between June 29 and July 18, 2026, are included in Attachment 5.  All subgrade density measurements exceeded the required minimum density.

Field density testing of the subgrade and structural fill was performed by the RPR (Kyle Bridges) using a nuclear density gauge, with the maximum dry density established by a one-point Michigan Cone test.

An Atlas Copco Dynapac CA2500 smooth drum vibratory roller, with an operating weight of 22,266 pounds, was used to proof-roll the subgrade prior to acceptance.  Visual observation during proof-rolling indicated no ruts or deformities were created in excess of 0.1’.

## Certification & Acceptance

The subgrade elevation in the northwestern portion of the cell was changed from the original construction plans to match the existing, as-built subgrade elevation of Cell B-1.  This change was discussed with EGLE on July 21 and documented to EGLE in a July 23 email (see Attachment 3).

Certification survey for the subgrade occurred during three mobilizations.  The multiple mobilizations occurred, in part, due to the subgrade discrepancy between adjacent Cell B-1.  Subgrade survey work was completed by Gosling Czubak survey personnel on July 20, July 26, and August 9, 2026.  Survey measurements were taken using a GNSS real-time kinematic survey-grade GPS receiver manufactured by Leica Geosystems.  The August mobilization was completed concurrently with the survey certification of the secondary liner system after the temporary access road was removed, allowing access to the subgrade in the southeast corner of the cell.  Subgrade record elevations are presented on Sheet 4D in Attachment 1.

The subgrade was found to meet the acceptance criteria outlined in Section 4.4 of the CQA Plan.  Specifically:

- Visual inspection did not identify any anomalous soils or ill-suited materials

- Density test measurements met the project requirement of at least 95% of the standard Proctor maximum dry density (ASTM D698)

- Fill materials met applicable pre-qualification test requirements for grain size

- Proof-rolling did not result in any deformities greater than 0.1’

- Survey elevations were within tolerance of the design grade, after adjusting the northwestern slope to match Cell B-1

# Secondary liner system

The secondary liner consists of a geosynthetic clay liner (GCL), a 60-mil textured HDPE geomembrane, and a geonet drainage composite (secondary leak-detection layer) as shown in the Proposed Cell Bottom Construction Detail and Typical Cell Sideslope Construction Detail on Sheet 6 in Attachment 1.  Preconstruction submittals, installation methods, testing results, and certification of the secondary liner system are presented in the following sections.

## Geosynthetic Clay Liner (GCL)

### Prequalification Data

CAAWS submitted prequalification data for one hundred ten rolls of Solmax Bentoliner NS 75 PEEL 35 needle-punched, reinforced geosynthetic clay liner (GCL) (product code 1130008), manufactured by Solmax Geosynthetics LLC of Spearfish, South Dakota.  The GCL consists of granular sodium bentonite encapsulated between a woven carrier geotextile on the bottom and a nonwoven cap geotextile on the top.  Attachment 7 includes the following submittal data required by Section 7.1 of the CQA Plan:

- Roll quality control certificates confirming that a representative sample of the GCL meets the minimum project requirements;

- Signed manufacturer's certification that the minimum values in Table 4 are met;

- Manufacturing quality control (MQC) manual and material data sheet;

- Manufacturer's qualifications (Solmax project list) and installer's qualifications (CAAWS project reference list);

- Manufacturer's recommendations for installation and anchoring; and

- Interface shear strength documentation, as summarized in Section 4.2.1.

The GCL rolls are numbered 0242-457138 through 0242-457249 (0242-457156 and 0242-457203 are not included), totaling one hundred ten rolls and a nominal 341,000 square feet at 3,100 square feet per roll (15.5 feet wide by 200 feet long), and were produced on April 29 and April 30, 2026.  All one hundred ten rolls met or exceeded the minimum project requirements summarized in Table 4, as documented in the manufacturer's roll and bentonite-lot certifications (Solmax MQC report dated April 30, 2026).  The bentonite used to produce the project rolls was drawn from seven lots, each of which met the swell index (≥ 24 mL/2 g, ASTM D5890), fluid loss (≤ 18 mL, ASTM D5891), and moisture content (≤ 12%) requirements.

The GCL material data sheet, MQC manual, and project reference list were reviewed against Section 7.1 of the CQA Plan and released for production on March 31, 2026, with acceptance pending the results of the interface friction analysis.  The manufacturer's roll certifications were subsequently submitted on May 11, 2026 and approved as noted by the CQA Officer on May 26, 2026, with the condition that the material not be shipped more than one month prior to installation.

Table 4 GCL Prequalification Data Summary

| Material Property | Test Method | CQA Plan Requirement | Test Frequency | Manufacturer's Certified Value | Pass/ Fail |
| --- | --- | --- | --- | --- | --- |
| Bentonite Fluid Loss | ASTM D5891 | 18 mL maximum | 1 per 50 tons | ≤ 18 mL (14.6–15.6 mL, MQC lots) | Pass |
| Bentonite Moisture Content | ASTM D2216 | 12% maximum | 1 per 50 tons | ≤ 12% (9.1–10.8%, MQC lots) | Pass |
| GCL Grab (Wide-Width Tensile) Strength | ASTM D6768 | 30 lb/in minimum | 1 per 200,000 ft2 | 30 lb/in min.; ≥ 43 lb/in (MQC) | Pass |
| GCL Peel Strength | ASTM D6496 | 3.5 lb/in minimum | 1 per 40,000 ft2 | 5.3 lb/in min.; ≥ 7.6 lb/in (MQC) | Pass |
| Bentonite Mass per Unit Area3 | ASTM D5993 | 0.75 lb/ft2 minimum | 1 per 40,000 ft2 | 0.75 lb/ft2 min.; ≥ 0.79 lb/ft2 (MQC) | Pass |
| GCL Hydraulic Conductivity | ASTM D5887 | 5.0 × 10-9 cm/sec maximum | 1 per 250,000 ft2 | ≤ 5.0 × 10-9 cm/sec | Pass |
| GCL Hydrated Internal Shear Strength | ASTM D6243 | 500 lb/ft2 @ 200 lb/ft2 normal force | 1 per 1,000,000 ft2 | 5,279 lb/ft2 @ 200 lb/ft2 (Geotechnics L26-112-008) | Pass |

Interface shear strength between the GCL and the adjacent liner-system components was evaluated by Geotechnics, Inc. in accordance with ASTM D5321 and ASTM D6243 and is summarized in Section 4.2.1 (Table 6).

Internal shear strength testing of the geosynthetic clay liner (GCL) was performed by Geotechnics, Inc. in accordance with ASTM D6243 (Project No. L26-112-008; Solmax NS 75 Peel 35 GCL, Roll No. 0250-000030; specimen inundated with water and seated 24 hours prior to shearing; approved September 11, 2026).  The measured peak internal shear strength exceeded the CQA Plan requirement of 500 pounds per square foot at a 200-pound-per-square-foot normal load, and the GCL met the internal shear strength acceptance criterion.

### Delivery & Storage

The GCL was delivered to the project site on the delivery date or dates shown on the GCL shipping papers in Attachment 8.  Each roll was wrapped in a waterproof, ultraviolet-resistant covering and labeled with the manufacturer's name, product identification, lot and batch numbers, date of fabrication, roll number, and roll dimensions.  The RPR visually inspected each roll upon delivery for packaging or material damage and confirmed that the delivered roll numbers matched those listed on the manufacturer's quality control certificates. Rolls were stored no more than three high and protected from ultraviolet exposure, precipitation, and other sources of moisture with an additional tarpaulin, in accordance with ASTM D5888 and the manufacturer's recommendations.  Shipping papers for the GCL were gathered by the RPR and are provided in Attachment 8.

### Deployment

Prior to deployment of the secondary GCL, the underlying prepared subgrade was inspected and accepted for installation.  Deployment of the secondary GCL began on August 1, 2026, as recorded in the GCL placement records in Attachment 9 and the daily construction reports in Attachment 2 and proceeded from high to low elevation where practical.

CAAWS utilized a telehandler with a spreader bar to position and support the GCL rolls at the cell perimeter during deployment.  Rolls were unrolled by pulling the leading edge manually or with a winch so as not to damage the prepared subgrade.  The GCL was deployed with the woven carrier side down against the underlying surface and the nonwoven cap side facing up.  Panels were deployed to minimize wrinkles and were not trafficked by construction equipment.  Secondary GCL panels were labeled in the field sequentially as the panel numbers listed in the GCL panel placement log in Attachment 9.  Sheet number (fill this in from the record drawings) of Attachment 1 shows the panel placement diagram and associated panel numbers.  The GCL panel placement log, which cross-references field panel number with the manufacturer’s roll number, is included in Attachment 9.

During deployment, the panels were shingled in the down-slope direction so that overlaps drained from the upper panel to the lower panel.  The GCL panels were inspected during and after placement for tears, thin spots, premature hydration, and proper overlap, and any damaged areas were marked for repair.

### Seaming

GCL panels were overlapped at least 6” in the machine direction (length) and 12” in the transverse direction (width).  A continuous line of granular bentonite was placed in the overlap area on the lower GCL panel.  GCL panels were shingled in the down-slope direction.

### In Place Testing

Unlike a compacted soil liner, the GCL is a manufactured product for which conformance is established primarily through the manufacturer's quality control certifications (Section 4.1.1) and field inspection during deployment; density, moisture, and flex-wall permeability testing are not applicable to the GCL.  The RPR visually inspected each deployed panel for tears, thin spots, and premature hydration, confirmed panel orientation and overlap widths, and verified that damaged areas were repaired in accordance with the manufacturer's recommendations prior to being covered.

| Sample / Roll ID | Test | Method | Result | Requirement | Pass/ Fail |
| --- | --- | --- | --- | --- | --- |
| the GCL sample or roll number tested, from the GCL submittal records in Attachment 7 | the property that was tested, such as bentonite mass or peel strength (Attachment 7) | the ASTM test method used (Attachment 7) | the measured test result (Attachment 7) | the minimum value required by the CQA Plan | whether the result passed or failed |

Table 5 GCL Conformance Testing Results

### Geosynthetic Clay Liner Acceptance

The deployed GCL was inspected and accepted prior to placement of the overlying 60-mil textured HDPE geomembrane.  Laboratory certifications, visual inspection, and field records were compared to the acceptance criteria of Section 7 of the CQA Plan, and the GCL was found to meet all acceptance criteria.  Specifically:

- The manufacturer's roll and bentonite-lot certifications met or exceeded all minimum project requirements (Table 4);

- Interface and internal shear strength results met the design requirements (Table 6 and Section 4.1.1);

- The GCL was deployed with the correct orientation and overlaps and was not trafficked by construction equipment;

- Damaged areas and any premature hydration were repaired prior to covering; and

- The CQA Officer's written acceptance of the interface-friction condition placed on the GCL submittal (March 31, 2026) is documented.

The GCL surface was accepted by the geomembrane installer, Clean Air and Water Systems (CAAWS), prior to installation of the geomembrane.

## Geomembrane

### Prequalification Data

CAAWS submitted prequalification data for thirty-three rolls of 60 mil textured high density polyethylene (HDPE) geomembrane manufactured by SKAPS Industries of Commerce, Georgia (product HD-60T2 AVG, textured both sides).  Attachment 10 includes the following submittal data required by Section 8.1 of the CQA Plan:

- Manufactured geomembrane properties

- Raw resin properties

- Manufacturer’s qualifications (SKAPS project list) and installer’s qualifications (CAAWS project reference list)

- Installation crew resumes

- Proposed panel layout (CAAWS Drawing P-1, drawn February 27, 2026)

- Geomembrane installation and quality control manual (CAAWS)

The geomembrane rolls are numbered 3119013890 through 3119013923 (3119013893 is not included), totaling 380,160 square feet, and were all produced from Formosa Plastics resin lot 26B1071.  All 33 rolls met the manufacturer’s published properties for HD-60T2 AVG.

Representative samples of the liner-system materials — the native subgrade soil, the geosynthetic clay liner (GCL), the 60-mil textured HDPE geomembrane, the geocomposite, and the drainage sand — were submitted to Geotechnics, Inc. of East Pittsburgh, Pennsylvania for interface friction testing under Project No. L26-112-001 (ASTM D5321 for soil and sand interfaces; ASTM D6243 for GCL interfaces).  Laboratory results for the interface testing are provided in Attachment 11 and summarized in Table 6.  It is required by the design that the tested interface friction between the liner system components be no less than the calculated shear resistance based on the following formula:

τ=σntanφ+α

where 	φ = friction angle (20°)

σn = applied normal load (1,000; 5,000; and 10,000 #/ft2)

α = adhesion (zero)

Table 6 Interface Friction Results Summary

| Interface | Laboratory Shear Stresses (psf, Peak) |  |  |
| --- | --- | --- | --- |
|  | 1,000 psf normal force | 5,000 psf normal force | 10,000 psf normal force |
| Native Soil vs. GCL (Woven Side) | 537 | 2,913 | 5,015 |
| GCL (Non-Woven Side) vs. 60-mil Textured HDPE | 662 | 2,293 | 4,070 |
| GCL (Woven Side) vs. Geocomposite | 587 | 2,322 | 4,238 |
| Geocomposite vs. 60-mil Textured HDPE | 596 | 2,314 | 4,467 |
| Drainage Sand vs. Geocomposite | 770 | 3,500 | 6,823 |
| Required Minimum Shear Strength (Calculated) | 363.9 | 1,819.8 | 3,639.7 |
| Pass/Fail? | Pass | Pass | Pass |

Based on the submittal data, the geomembrane submittal was approved as noted by the CQA Officer on March 19, 2026, and the manufacturer’s material certifications were approved as noted on May 27, 2026, with the condition that the material not be shipped more than one month prior to installation.

Interface shear strength testing for the liner system was performed by Geotechnics, Inc. (Project No. L26-112-001) in accordance with ASTM D5321 and ASTM D6243, with each interface loaded, inundated, and sheared at normal loads of 1,000, 5,000, and 10,000 psf; the results were approved by the CQA Officer on June 25, 2026.  The peak shear stresses for every tested interface exceed the required minimum shear strength at all three normal loads (Pass).  For the Native Soil / GCL and GCL / Geocomposite interfaces, the failure occurred by internal shearing of the GCL at the 10,000 psf normal load, and the reported values represent that internal-shear condition.

### Delivery & Storage

Geomembrane was delivered to the project site on April 10, 2026.  Geomembranes were unloaded using the manufacturer provided lifting straps and stacked, up to three rolls high, on a 6-8” thick sand base prepared by M&M Excavating.  The RPR inspected the rolls upon delivery for any damage that may have resulted during transport and to confirm the delivered material matched the roll numbers proposed by CAAWS.  Shipping papers for the geomembrane were gathered by the RPR and are provided in Attachment 12.

### Deployment

Deployment of the secondary geomembrane began on August 1, 2026, as shown in the secondary geomembrane panel placement and seaming summary in Attachment 13 after the underlying GCL was inspected and accepted for installation.

CAAWS utilized a telehandler with a spreader bar to position and support the geomembrane rolls at the cell perimeter during deployment.  Rolls were unrolled by pulling the leading edge with an ATV when doing so would not damage the underlying GCL nor damage adjacent geomembrane.  Unrolling manually and with a winch were other methods used to place the geomembrane.  Secondary panels were labeled in the field sequentially as S1 through S47.  Sheet 10 of Attachment 1 shows the panel placement diagram and associated panel numbers.  The panel placement log, which cross-references field panel number with the manufacturer’s roll number, is included in Attachment 13.

During deployment, the panels were overlapped in a shingled fashion to allow any fluids flowing across the seam to flow downhill, from the top panel to the lower panel.  The geomembrane panels were inspected during and after placement for uniformity, damage, and imperfections.  Any imperfections were marked for repair.

### Seaming

CAAWS utilized both extrusion and fusion welds to complete the secondary liner, with fusion welding being the primary welding method.  Extrusion welding was used to make repairs and complete the tie-in to the existing secondary liner of Cell B-1.  Seaming was only completed in weather conditions that would not impair the quality of the weld.

Prior to welding the secondary geomembrane, trial welds were completed on each machine-operator combination.  Destruct samples were taken from the trial welds and tested in the field by CAAWS using a DemTech Pro-Tester T-0100 tensiometer.  Test results were compared to the seam strength requirements in Table 8-E of the CQA Plan.  Any failing tests resulted in CAAWS inspecting and retesting the machine-operator combination.  A failing machine-operator combination was not allowed to weld geomembrane.  This information is also provided in Attachment 13.

The panel seaming summary, which identifies the machine and operator used to complete each seam, is included in Attachment 13.  The different machine and operator codes used in the panel seaming summary are provided in Table 7.

Table 7 Seaming Personnel & Equipment

| Operator Initials | Operator Name |  | Machine Code | Machine Type |
| --- | --- | --- | --- | --- |
| RM |  |  | 6050 | DemTech VM-20 (Fusion) |
| HL |  |  | 6416 | DemTech VM-20 (Fusion) |
|  |  |  | 94 | DemTech X-5 (Extrusion) |
|  |  |  | 292 | DemTech X-5 (Extrusion) |

#### Nondestructive Testing

Non-destructive testing was completed over the full length of all field seams and repairs to verify their integrity.  The RPR observed the test procedures and results to ensure compliance with the CQA Plan.  Air pressure tests were completed on all dual-track fusion welds; extrusion welds were tested using a Demtech V-Plate vacuum box.  The field-testing records provided in Attachment 14 indicate that all seams passed the non-destructive testing.

#### Destructive Testing

The RPR selected destruct samples for quantitative testing of the geomembrane seam strength.  Sample locations were selected at a frequency of at least one sample per seaming crew-machine combination, or at least one every 500’ of seam, which ever was greater.  Destruct sample locations are shown on Sheet 10 in Attachment 1.

Destruct samples were cut into three fractions, each approximately 15” long by 12” wide, for field testing, third-party laboratory testing, and archiving in accordance with ASTM Standard D6392.  Field testing was completed by CAAWS using a tensiometer; third-party testing was completed by Geotechnics, Inc..  Results of destructive testing are provided in Attachment 15.

### Defects & Repair

DS-9, along seam 23/24, was the only destruct sample from the secondary liner to fail either the field or laboratory destruct testing.  Adjacent samples, DS-9A and DS-9B, were taken approximately 10’ either side of the original DS-9.  These samples both passed destruct testing.  The seam between DS-9A and DS-9B was capped.

In all, 103 repairs were made to the secondary geomembrane liner.  These repairs were necessitated by a variety of conditions, including:

- Multiple panels intersecting

- Machine burn through

- Destruct sample locations

- Air test holes

- Tears, holes, or rips

- Manufacturer defect

Repairs were made by capping the area with geomembrane that extended at least 6” beyond the edge of the defect.  The cap was extrusion welded in place.  All repairs were tested by vacuum box testing.  The field repair record of secondary geomembrane repairs is included as Attachment 16.

## Geocomposite

### Prequalification Data

CAAWS submitted prequalification data for one hundred thirty rolls of 300 mil geonet, encased on both sides with 8-ounce nonwoven polypropylene filter fabric (SKAPS TRANSNET TN 330-2-8), manufactured by SKAPS Industries of Commerce, Georgia.  Submittal data required by Section 9.1 of the CQA Plan, which included the following information, is provided in Attachment 17:

- Manufactured geocomposite properties

- Geonet properties

- Filter fabric properties

- Raw resin properties

- Resin supplier information

The geocomposite rolls are numbered 164311230001 through 164311230130 and were produced from Bayport Polymers resin lot FUNX 901012.  The material data sheet was approved by the CQA Officer on March 19, 2026, and the manufacturer’s material certifications were approved as noted on May 26, 2026, with the condition that the material not be shipped more than one month prior to installation.

### Delivery & Storage

Geocomposite rolls were delivered to the project site on the delivery date shown on the geocomposite shipping papers in Attachment 18.  These rolls were stored in the same manner as the geomembrane described in Section 4.2.2.  The RPR was not onsite at the time of delivery.  The rolls were inspected prior to deployment for any damage that may have resulted during transport, storage, and to confirm the delivered material matched the roll numbers proposed by CAAWS.  Shipping papers for the geocomposite were gathered by the RPR and are provided in Attachment 18.

### Deployment

CAAWS utilized a telehandler with a spreader bar to position and support the geocomposite rolls at the cell perimeter during deployment.  Rolls were unrolled by pulling the leading edge manually or with a winch to prevent damage to underlain geomembrane.  Geocomposite was positioned in the same general orientation as the geomembrane with seams following the fall line.  The following geocomposite rolls were used:

Table 8 Secondary Geocomposite Roll List

| INSTALLATION DATE |  |  |
| --- | --- | --- |
| [INSERT 2026 installation date] | [INSERT 2026 installation date] | [INSERT 2026 installation date] |
| the actual roll number used, in the 164311230001 to 164311230130 range, from the geocomposite shipping papers in Attachment 18 and the field placement records in Attachment 2 | the actual roll number used, in the 164311230001 to 164311230130 range, from the geocomposite shipping papers in Attachment 18 and the field placement records in Attachment 2 | the actual roll number used, in the 164311230001 to 164311230130 range, from the geocomposite shipping papers in Attachment 18 and the field placement records in Attachment 2 |

### Seaming

Geocomposite rolls were overlapped at least 6” in the machine direction (length) and 24” in the transverse direction (width) to allow for seaming.  The geonet of adjacent panels were secured using white zip-ties placed every 5’ in the machine direction and every 12” in the transverse direction.  The upper filter fabric of the geocomposite was sewn to the fabric of the adjacent panel along the panel length using a hand-held Newlong NP-3ii industrial sewing machine with white thread.  At the transverse end, a continuous piece of filter fabric was heat tacked over the seam to prevent soil material from entering the geonet.

### Defects & Repair

Visual inspection of the geocomposite prior to, during, and after placement did not identify any defects or areas requiring repair.  Adequate overlap was provided between adjacent panels and seaming provided a continuous geocomposite drainage layer.

## Leak Detection System

The secondary leak detection system is comprised of a geonet drainage composite over the cell floor, an 8” HDPE collection pipe, and coarse drainage aggregate.

### Prequalification Data

The sand used for the secondary leak detection drainage layer was a washed “2NS” sand provided by Lewiston Sand & Gravel Buttles Road Pit.  Samples of the material were collected by the RPR for laboratory analysis by GCES (grain size and hydraulic conductivity) and Bowser-Morner, Inc. (BMI, carbonate content).  The secondary drainage sand samples are identified as samples #7 (2NS-A) and #8 (2NS-B) in the laboratory reports of Attachment 19.  A summary of the results is provided in Table 9.

Table 9 Secondary Drainage Sand Prequalification Summary

|  | #7 ‘2NS - A’ | #8 ‘2NS - B’ | CQA Plan Requirements | Pass/Fail |
| --- | --- | --- | --- | --- |
| USCS Classification | Sand, Poorly Graded (SP) | Sand, Poorly Graded (SP) | Refer to Table 10-B in CQA Plan | Pass |
| Hydraulic Conductivity (cm/sec) | 2.73 x 10-2 | 2.65 x 10-2 | > 1.0 x 10-2 | Pass |
| Carbonate Content | 0.1% | 0.1% | < 10% | Pass |

The coarse aggregate used around the collection pipe within the leachate collection trench was a washed MDOT “6A” stone provided by Lewiston Sand & Gravel from their Buttles Road Pit.  Samples of the material were submitted by GCES to Geotechnics, Inc. of East Pittsburgh, Pennsylvania for carbonate content (ASTM D3042) and hydraulic conductivity (ASTM D2434, constant head) testing.  The drainage stone samples are identified as Samples 1, 5, and 6 in the laboratory report (Geotechnics Project No. 2026-435-001, dated June 9, 2026).  Laboratory reports are provided in Attachment 20 and summarized in Table 10.

Table 10 Drainage Stone Prequalification Summary

|  | 6A Samples 1, 5 & 6 | CQA Plan Requirements | Pass/Fail |
| --- | --- | --- | --- |
| USCS Classification | Not reported | Refer to Table 10-C in CQA Plan | Pending |
| Hydraulic Conductivity (cm/sec) | 1.1 x 101 to 2.1 x 101 | > 1.0 x 10-2 | Pass |
| Carbonate Content | 0.0% to 0.1% | < 10% | Pass |

High density polyethylene (HDPE) 8” diameter DR 17 (IPS) pipe, meeting the ASTM D3350 classification for PE4710 (minimum cell classification 445574C), was used for the leachate collection and conveyance system.  The pipe, manufactured by ISCO, was perforated in accordance with the approved ISCO shop drawing (part no. 35081799; four rows of 3/8-inch diameter holes at 6 inches on center) to meet the perforation detail on Sheet 8.  Submittal information for the pipe is provided in Attachment 21.  The RPR inspected the pipe upon arrival for damage and to confirm that the material met the project requirements.  The pipe material was covered and stored in accordance with the CQA Plan.

The 18-inch DR 17 perforated sump pipe (ISCO part no. 35181799; six rows of 3/8-inch diameter holes at 6 inches on center) and the fabricated 18-inch DR 17 primary and secondary sump bottom assemblies were also supplied by ISCO.  The ISCO HDPE pipe and fittings submittal, including the associated PVC, stainless steel, and valve components, was approved by the CQA Officer, with approval stamps dated May 11 and May 14, 2026.

### Placement

Drainage sand was placed on the geocomposite beginning September 14.  An excavator was initially used to place the sand by dropping it from just above the geocomposite surface.  This was done to reduce the risk of causing wrinkles or folds by pushing the geocomposite.  A minimum sand thickness of 3’ was maintained along the south edge of the cell and east edge of the leachate trench so that larger equipment could access the area to install the leachate pipe and stone.  The drainage stone was placed 12” thick and covered with geocomposite.  CAAWS secured the geocomposite over the drainage stone using the same methods described in Section 4.3.4.  A calculated ±1,367 cubic yards of drainage sand and ±28 cubic yards of stone were placed in the secondary leak detection system.

### Testing

Density and thickness of the drainage sand was tested by the RPR on an approximately 100’x 100’ grid.  Density was measured using a Troxler Model 3440 nuclear density gauge (ASTM D6938) and recorded.  In accordance with Addendum No. 2 (Response 7a), the 95 percent maximum dry density specified for the drainage material is a laboratory performance standard and is not a field compaction requirement.  The sand thickness was measured at 1’ ±0.1’.  These measurements were completed on September 18, 2026 and are reported in the associated Construction Observation (Attachment 2) and Density (Attachment 5) Reports.

The solid section of leachate pipe was air tested in place along Station 20+00 on the north slope.  The air test began at 9.5 psi and remained, unchanged, for 1 hour.  Air testing occurred on September 20, 2026.

### Defects & Repair

Visual inspection prior to, during, and after placement did not identify any defects or areas requiring repair.  The material used in the leak detection system met the requirements of the CQA Plan.

# Primary Liner System

The primary liner consists of a geosynthetic clay liner (GCL) across the cell floor and side slopes, a 60-mil textured HDPE geomembrane, a geonet drainage composite, 24” of drainage sand, and an 8-ounce non-woven filter fabric as shown in the details on Sheet 6 in Attachment 1.  Preconstruction submittals, installation methods, testing results, and certification of the primary liner system are presented in the following sections.  Many of the same materials used in the secondary liner system were used in the primary system.

## Geosynthetic Clay Liner (GCL)

### Prequalification Data

CAAWS submitted prequalification data for one hundred ten rolls of Bentoliner NS 75 PEEL 35 (product code 1130008) geosynthetic clay liner (GCL) manufactured by Solmax of Spearfish, South Dakota.  Submittal data required by Section 7.1 of the CQA Plan, which included the following information, is provided in Attachment 7:

- Roll allocation list

- Roll quality certificates

- Raw bentonite properties

- Bentonite supplier information

The geosynthetic clay liner supplied for the primary liner system is the same product and manufacturer's order described for the secondary liner system in Section 4.1.1; the 110-roll order (nominal 341,000 square feet) supplied the GCL for both the primary and secondary liner systems.  The specific rolls deployed in the primary liner system are identified in the GCL panel placement log in Attachment 9. Confirm this roll list against the GCL panel placement log in Attachment 9.  The initial GCL submittal was approved as noted and released for production by the CQA Officer on March 31, 2026, with acceptance pending the results of the interface friction analysis.  The roll certifications were approved as noted on May 26, 2026, with the condition that the material not be shipped more than one month prior to installation.  All 110 rolls met the certified minimum bentonite mass (0.75 lb/ft2), peel strength (35 lbf by ASTM D4632 and 5.3 lbf/in by ASTM D6496), and machine-direction tensile strength (30 lbf/in).  All seven bentonite lots met the swell index (24 mL/2 g minimum), moisture content (12% maximum), and fluid loss (18 mL maximum) requirements.

### Delivery & Storage

GCL was delivered to the project site on September 4, 2026.  These rolls were stored in the same manner as the geomembrane as described in Section 4.2.2.  The RPR inspected the rolls during unloading for any damage that may have resulted during transport and to confirm the delivered material matched the roll numbers proposed by CAAWS.  Shipping papers for the GCL were gathered by the RPR and are provided in Attachment 8.

### Deployment

Precipitation in late September and October delayed and slowed deployment of the primary GCL and the overlying geomembrane.  Deployment of the primary GCL began on the start date recorded in the GCL placement records in Attachment 9 (or the daily construction reports in Attachment 2) after the underlying surface was inspected and accepted for installation.

CAAWS utilized a telehandler with a spreader bar to position and support the GCL rolls at the cell perimeter during deployment.  Rolls were unrolled by pulling the leading edge manually or with a winch to prevent damage to the underlying geocomposite.  The GCL was deployed with the woven carrier side down and the nonwoven cap side up, positioned in the same general orientation as the geomembrane, and was covered with geomembrane the same day it was laid to prevent premature hydration of the bentonite.  The GCL extended from the back edge of the anchor trench to at least 5’ onto the cell floor, and along the western and eastern berms the GCL of Cell B-1 was shingled over the new GCL in Cell C - Phase I.  Primary GCL panels were labeled in the field sequentially as the panel numbers listed in the GCL panel placement log in Attachment 9.  Sheet number (fill this in from the record drawings) of Attachment 1 shows the panel placement diagram and associated panel numbers.  The GCL panel placement log, which cross-references field panel number with the manufacturer’s roll number, is included in Attachment 9.

During deployment, the panels were shingled in the down-slope direction, and the GCL panels were inspected during and after placement for tears, thin spots, premature hydration, and proper overlap.  Any damaged areas were marked for repair.

### Seaming

GCL panels were overlapped at least 6” in the machine direction (length) and 12” in the transverse direction (width).  A continuous line of granular bentonite was placed in the overlap area on the lower GCL panel.  GCL panels were shingled in the down slope direction.

### Defects & Repair

Visual inspection of the GCL prior to, during, and after placement did not identify any defects or areas requiring repair.  Adequate overlap was provided between adjacent panels and seaming provided a continuous GCL layer.

## Geomembrane

Submittal information for the geomembrane material used in the primary liner system is included with the secondary geomembrane data in Attachments 10 – 12 and Table 6.  The storage methods were as described in Section 4.2.2.

### Deployment

Precipitation in late September and October delayed and slowed the deployment of the primary geomembrane and associated underlying GCL.  Deployment of the primary geomembrane began on the western edge and slope on September, 2026.  The underlying GCL surface was inspected and accepted for installation in two phases; the western portion was accepted October 1, the eastern half on October 10.  The final primary geomembrane panels were installed on October 13, 2026.

The geomembrane panels were deployed in the same manner as the secondary geomembrane.  Primary panels were labeled in the field sequentially as P1 through P56.  Sheet 11 of Attachment 1 includes the panel placement diagram and associated panel numbers.  The panel placement log, which cross-references field panel number with the manufacturer’s roll number, is included in Attachment 23.

During deployment, the panels were overlapped in a shingled fashion to allow any fluids flowing across the seam to flow downhill, from the top panel to the lower panel.  The geomembrane panels were inspected during and after placement for uniformity, damage, and imperfections.  Any imperfections were marked for repair.

### Seaming

CAAWS utilized both extrusion and fusion welds to complete the primary liner, with fusion welding being the primary welding method.  Extrusion welding was used to make repairs and complete the tie-in to the east half of Cell B-1 primary liner.  Seaming was only completed in weather conditions that would not impair the quality of the weld.

Prior to welding the primary geomembrane, trial welds were completed on each machine-operator combination.  Destruct samples were taken from the trial welds and tested in the field by CAAWS using a DemTech Pro-Tester T-0100 tensiometer.  Test results were compared to the seam strength requirements in Table 8-E of the CQA Plan.  Any failing tests resulted in CAAWS inspecting and retesting the machine-operator combination.  A failing machine-operator combination was not allowed to weld geomembrane.  This information is also provided in Attachment 23.

The panel seaming summary, which identifies the machine and operator used to complete each seam, is included in Attachment 23.  The different machine and operator codes used in the panel seaming summary are provided above in Table 7.

#### Nondestructive Testing

Non-destructive testing was completed over the full length of all field seams and repairs to verify their integrity.  The RPR observed the test procedures and results to ensure compliance with the CQA Plan.  Air pressure tests were completed on all dual-track fusion welds; extrusion welds were tested using a vacuum box.  The field-testing records provided in Attachment 24 indicate that one seam failed nondestructive testing by air channel testing.  This seam, WT/1, is where the liners of Cell C - Phase I and Cell B-1 connect.  The area was later capped, and vacuum box tested.

#### Destructive Testing

The RPR selected destruct samples for quantitative testing of the geomembrane seam strength.  Sample locations were selected at a frequency of at least one sample per seaming crew-machine combination, or at least one sample every 500’ of seam, whichever was greater.  Destruct sample locations are shown on Sheet 11 in Attachment 1.

Destruct samples were cut into three fractions, each approximately 15” long by 12” wide, for field testing, third-party laboratory testing in accordance with ASTM Standard D6392, and archiving.  Field testing was completed by CAAWS using a tensiometer; third-party testing was completed by Geotechnics, Inc..  Results of destructive testing are provided in Attachment 25.

### Defects & Repair

Destruct samples from two primary liner seams failed destruct sampling; seam 37/38, and a portion of the seam along the tie-in to Cell B-1.  The failing test on seam 37/38, DS-12, was bound by two passing tests (DS-12A and DS-12B) and the area capped.  Adjacent samples to the failing south tie-in test location (DS-29A and DS-29B) were taken approximately 10’ either side of the original DS-29.  Neither of these samples passed destruct testing.  A third destruct sample (DS-31), taken approximately 20’ west of DS-29A passed destructive testing.  The entire seam east of DS-31 was capped to the eastern edge of the liner system.

In all, 128 repairs were made to the primary geomembrane liner.  These repairs were necessitated by a variety of conditions, including:

- Multiple panels intersecting

- Machine burn through

- Destruct sample locations

- Air test holes

- Tears, holes, or rips

- Leachate pipe boot

Repairs were made by capping the area with geomembrane that extended at least 6” beyond the edge of the defect.  The cap was extrusion welded in place.  All repairs were tested by vacuum box testing.  The field repair record of primary geomembrane repairs is included as Attachment 26.

## Geocomposite

Submittal information for the geocomposite material used in the primary liner system is included with the secondary geocomposite data in Attachments 17 and 18.  The storage methods were as described in Section 4.3.2.

### Deployment

Geocomposite was placed on the floor and approximately 5’ up onto the slopes of the primary liner.  Geocomposite rolls were deployed in the same manner as the secondary geocomposite.  The following geocomposite rolls were used:

Table 11 Primary Geocomposite Roll List

| INSTALLATION DATE |  |
| --- | --- |
| 2026 installation date | 2026 installation date |
| the actual roll number used, in the 164311230001 to 164311230130 range, from the geocomposite shipping papers in Attachment 18 and the field placement records in Attachment 2 | the actual roll number used, in the 164311230001 to 164311230130 range, from the geocomposite shipping papers in Attachment 18 and the field placement records in Attachment 2 |

### Seaming

Geocomposite rolls were overlapped at least 6” in the machine direction (length) and 24” in the transverse direction (width) to allow for seaming.  The geonet of adjacent panels were secured using white zip-ties placed every 5’ in the machine direction and every 12” in the transverse direction.  The upper filter fabric of the geocomposite was sewn with white thread to the fabric of the adjacent panel along the panel length.  At the transverse end, a continuous piece of filter fabric was heat tacked over the seam to prevent soil material from entering the geonet.

### Defects & Repair

Visual inspection of the geocomposite prior to, during, and after placement did not identify any defects or areas requiring repair.  Adequate overlap was provided between adjacent panels and seaming provided a continuous geocomposite drainage layer on the floor.

## Leachate Collection System

The primary leachate collection system is comprised of a 24” sand layer over the entire cell floor, an 8” HDPE collection pipe, and coarse drainage aggregate.

### Prequalification Data

The sand used for the primary leachate collection drainage layer was obtained from the Mathews Rd. source.  Samples of the material were submitted by GCES to Geotechnics, Inc. for hydraulic conductivity testing (ASTM D2434, constant head).  The primary drainage sand samples are identified as Samples 6 and 7 in the laboratory report of Attachment 19.  Measured hydraulic conductivity ranged from 2.1 x 10-2 to 2.5 x 10-2 cm/sec, which meets the CQA Plan requirement of at least 1.0 x 10-3 cm/sec for primary drainage sand.  Carbonate content and particle size distribution were not reported for the sand samples.  The particle size distribution limits, shown in Table 12, were revised from the CQA Plan.  The revision was discussed with EGLE prior to the material being placed in the field.

Table 12 Primary Drainage Sand Particle Size Distribution (Revised)

| SIEVE DESIGNATION | % PASSING BY WEIGHT |
| --- | --- |
| 1-inch | 100 |
| ½-inch | 85-100 |
| No. 4 | 75-100 |
| No. 10 | 60-95 |
| No. 40 | 0-55 |
| No. 100 | 0-15 |
| No. 200 | 0-5 |

The coarse aggregate and HDPE pipe used within the leachate collection trench around the collection pipe was the same material used for the secondary system.  Laboratory reports and submittal information are provided in Attachments 20 and 21.

The 8-ounce nonwoven filter fabric was Mirafi E800 manufactured by Propex Operating Company (a Solmax company).  Material certifications were submitted for thirty-nine rolls (roll nos. 2028186386 through 2028186425; 2028186422 is not included), all from production order 2334164, for a nominal total of 175,500 square feet.  All rolls met the manufacturer’s published properties.  The geotextile submittal was approved by the CQA Officer on March 19, 2026, and the material certifications were approved on May 27, 2026.  Submittal information is provided in Attachment 17 (best guess, based on the attachment list; verify).

Two EPG WSDPT SurePump wheeled sump drainers (Model 5-5, five impeller stages, 1 HP, 230 V single-phase) were furnished for installation in the side-slope risers, with a specified design duty point of 18 gpm at 100 feet total dynamic head.  The EPG SurePump was accepted as an approved substitution for the 0.50-horsepower A.Y. MacDonald (Baker Water Systems) submersible pump (17.5 gpm at 100 feet total dynamic head) specified in Section 11210 of the project specifications; the substitution was reviewed and approved as noted by the CQA Officer on the pump submittal dated April 15, 2026.  The pumps are operated by an EPG L975PT-2 control panel (EPG job no. S46760) Check whether one dual-pump control panel or two separate controllers were actually installed, since Addendum No. 2 (Response 1b) calls for two separate controllers; confirm against the pump and controls submittal in Attachment 27 and update this sentence to match with level control meters, flow-rate totalizers, and 1.5-inch stainless steel paddlewheel flow sensors.  The pump submittal was approved as noted by the CQA Officer on April 15, 2026.  The control panel drawing set, flow sensor, and motor-lead and sensor junction boxes (EPG BJBP500 and BJBO800B) were approved on July 10, 2026.  Submittal information is provided in Attachment 27 (best guess, Leachate Building, Pumps, Controls and Force Main Records; verify).

### Placement

Drainage sand was placed on the geocomposite beginning October 29.  An excavator was initially used to place the sand by dropping it from just above the geocomposite surface.  This was done to reduce the risk of creating any wrinkles or folds by pushing the geocomposite.  A minimum sand thickness of 3’ was maintained along the south edge and east edge of the leachate trench so that larger equipment could access the area to install the leachate pipe and drainage stone.  The drainage stone was placed 12” thick and covered with geocomposite.  M&M Excavating secured the geocomposite over the drainage stone using the same methods described in Section 4.3.4.

### Testing

Density and thickness of the drainage sand was tested by the RPR on an approximately 100’x100’ grid.  Density was measured using a Troxler Model 3440 nuclear density gauge (ASTM D6938) and recorded.  In accordance with Addendum No. 2 (Response 7a), the 95 percent maximum dry density specified for the drainage material is a laboratory performance standard and is not a field compaction requirement.  The sand thickness was measured at 2’ ±0.1’.  These measurements are reported in the associated Construction Observation (Attachment 2) and Density (Attachment 5) Reports.

The solid section of leachate pipe was air tested in place along Station 20+00 on the north slope.  The air test began at 8.0 psi and remained, unchanged, for 1 hour.  Air testing occurred on , 2026.

### Defects & Repair

Visual inspection prior to, during, and after placement did not identify any defects or areas requiring repair.  The material used in the leachate collection system met the requirements of the CQA Plan.

### Final Acceptance

The elevation of the drainage liner system was measured by GCES survey personnel on November 6 and 27, 2026.  The November 27 survey event was completed using aerial photography and photogrammetry.  The data was collected using a DJI Matrice 210 UAS and interpreted using Pix4Dmapper.  Record elevations are presented along with design elevations on Sheet 4A in Attachment 1.

# Additional Project Details

## Anchor Trench

The anchor trench was cut into the subgrade at the A+95 line along the north edge of the cell on September XX.  CAAWS extrusion welded the primary and secondary liners together on October 9.  All geosynthetic materials extended onto the bottom of the anchor trench; the secondary geomembrane turned upward at the back (north) edge of the trench.  The anchor trench was backfilled with onsite sand, which was compacted to a minimum 95% modified proctor density as determined by nuclear density gauge approximately every 50’ along the trench.

## Rain Flap

An interim berm was installed along the eastern edge of Cell C - Phase I.  The berm is covered by a 60-mil HDPE rain flap that was connected to the rain flap of Future Cell C-II and extends to the anchor trench.  The berm, built in accordance with Sheet 7 of Attachment 1, is ±5.0’ higher than the cell side slope.

## Drainage

The soils outside the cell boundaries were cut and sloped to drain storm water away from the cell and towards the stormwater basins.  Stone check dams were installed to reduce the risk of erosion damage within the stormwater ditches along the north and east perimeter of the cell.  These drainages can be seen in the overall site plan, Sheet 12 of Attachment 1.

# Operating License Application

An operating license application that includes the additional 2.64 acres of Cell C - Phase I is included with this CDR as Attachment 28.

Attachment 1

Record Drawings

Attachment 2

Construction Observation Reports

Attachment 3

EGLE Correspondence and Project Administration Records

Attachment 4

Subgrade Material Properties

Attachment 5

Density and Thickness Verification Test Records

Attachment 6

Subsurface Soil Acceptance Forms

Attachment 7

Geosynthetic Clay Liner Prequalification Submittals

Attachment 8

Geosynthetic Clay Liner Shipping Papers

Attachment 9

Geosynthetic Clay Liner Placement and Repair Records

Attachment 10

Geomembrane Prequalification Submittals

Attachment 11

Interface Friction Test Results

Attachment 12

Geomembrane Shipping Papers

Attachment 13

Secondary Geomembrane Panel Placement and Seaming Summary

Attachment 14

Secondary Geomembrane Non-Destruct Test Records

Attachment 15

Secondary Geomembrane Destruct Test Results

Attachment 16

Secondary Geomembrane Repair Records

Attachment 17

Geocomposite and Filter Geotextile Prequalification Submittals

Attachment 18

Geocomposite and Filter Geotextile Shipping Papers

Attachment 19

Sand Prequalification Data

Attachment 20

Drainage Stone Prequalification Data

Attachment 21

Leachate Pipe Material Submittals and Fusion Qualifications

Attachment 22

Pipe Fusion and Pressure Test Records

Attachment 23

Primary Geomembrane Panel Placement and Seaming Summary

Attachment 24

Primary Geomembrane Non-Destruct Test Records

Attachment 25

Primary Geomembrane Destruct Test Records

Attachment 26

Primary Geomembrane Repair Records

Attachment 27

Leachate Building, Pumps, Controls and Force Main Records

Attachment 28

License Application

Textured liner was used for both the sloped portion and floor portion of Cell C, Phase I.  This is a change from the original design and was submitted to EGLE on June 15, 2026 (see email correspondence in Attachment 3).

Manufacturer's certified values are from the Solmax BENTOLINER NS 75 PEEL 35 material data sheet (product 1130008) and the manufacturing quality control (MQC) roll and bentonite-lot certifications (Solmax MQC report dated April 30, 2026, covering 110 rolls).  Ranges shown are the governing MQC results (lowest for minimum requirements).

The manufacturer reported bentonite moisture content in accordance with ASTM D4643; the CQA Plan specifies ASTM D2216.  Both are accepted moisture-content methods; confirm equivalency is acceptable to the CQA Engineer.

Listed in CQA Plan Table 7-A as “Total Mass per Area”; the ASTM D5993 value certified and reported is the bentonite mass per unit area.

[VERIFY/UPDATE: this note reflects the prior geocomposite roll-number convention and conflicts with the roll numbering in Section 4.3.1 (164311230001 through 164311230130); revise to match the actual Cell C-Phase I placement records.]

Textured liner was used for both the sloped portion and floor of Cell C, Phase I.  This is a change from the original design and was submitted to EGLE on June 15, 2026 (see email correspondence in Attachment 3).

[VERIFY/UPDATE: this note reflects the prior geocomposite roll-number convention and conflicts with the roll numbering in Section 4.3.1 (164311230001 through 164311230130); revise to match the actual Cell C-Phase I placement records.]

#40 limits were changed from 0-45% to 0-55%